## Sheet1
Team Goals |  | November 06th | Identify functions needed (Read Communications Protocol) | November 13th | Writing functions | November 20th | 2025-11-10 | November 27th | Write Up - 1,500 Words | December 03rd
|  |  | Capable of homing and moving the arm |  | Building state machine and implementation |  | Testing regime
|  |  | Scoped out the required sensors |  |  |  | Analyse testing regime. Qualitative review. Also, how do enhacements better the system?
First attempt at communicating with Dobot
Map the full area of the dobot arm, define areas and read co-ordinates back.
Create paper cut-out with patterned grid
Responsibilities | Jordan
Tej
Michael
Tyler
Will

## Sheet2
Task | Start | End | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03
Subsidiary Tasks
Set up Gihtub repository | 2025-11-06 | 2025-11-06
Map the arm's articulated area | 2025-11-06 | 2025-11-13
Component Implementation
Scope and acquire necessary components | 2025-11-06 | 2025-11-13
Implement Ultra Sonic sensor |  | 2025-11-13
Implement RGB sensor | 2025-11-20 | 2025-11-27
Code Development
Achieve the homing function | 2025-11-06 | 2025-11-06
Create checksum process | 2025-11-06 | 2025-11-13
Obtain coordinates | 2025-11-13 | 2025-11-27
Create count | 2025-11-20 | 2025-11-27
Develop State Machine | 2025-11-13 | 2025-11-27
Use buttons | 2025-11-13 | 2025-11-27
Comment code | 2025-11-27 | 2025-12-02
Qualitative Review | 2025-11-27 | 2025-11-27